## Instructions
Use these steps to guide you through the assessment process
Example DAI-IRSA Plan / Example DAI-IRSA Steps
Activity | Description | Tools
Identify Key People | Identify who will coordinate for your unit, and who will approve the resulting Information Risk Management Program | Division Planning Tab
Preparation and Assembling the Team | Use the IRSA and DAI tabs to help you identify who in your unit to consult | Roll-out template DAI and IRSA tabs
Request access to Survey and Reports | Contact the DAI-IRSA team to request unit access to the Survey Tool and Reports | https://uoft.me/IRSA
Review and update data inventory | Individually, or as a team, review your data asset inventory, and update as needed; use the DAI tab to identify important assets to include | Data Asset Inventory survey form in REDCap & Tableau reports
Assessment of Current Activities, Identification of Gaps, & plans for the next year | Individually, or as a team, review your risk self-assessment, complete any unanswered questions and review and update responses from the previous year | IRSA Survey form in REDCAp & tableau reports
IRMP Approval | Review results of the DAI and IRSA with your unit leadership and obtain approval for your plans | Tableau Reports
Monitoring | Update your DAI and IRSA as needed throughout the year, as circumstances change | DAI and IRSA survey forms
DAI-IRSA Departmental or Unit Assessment Planning Template
How your unit approaches completion of the assessment is up to you and your leadership. Some units may choose to have all respondents meet together to complete the assessment, others may decide to have each respondent login to the assessment tool separately and complete the section for which they are responsible. Depending on the size and complexity of your organization, completing the DAI-IRSA may involve one or two people or a larger number from the different functional groups represented in your unit. The deadline for completion of the inventory and assessment is January 31 each year.
Use this template to assist you in rolling out the DAI-IRSA in your Unit or Department. Your first step will be to review the timelines and define your approach:
Step 1: Review the timelines and important dates for the DAI-IRSA Program (Timeline Tab)
Step 2: In consultation with your leadership, determine who will be responsible for approving your unit's Information Risk Management Program
Step 3: Identify an individual to coordinate the completion of your unit's DAI-IRSA
Step 4: Use the Unit Planning and IRSA and DAI tabs to help you identify contributors from your team
Step 5: Determine who in your unit will have access to your unit's DAI-IRSA reports in tableau
Step 6: Inform the DAI-IRSA team of any access or permissions you require for the surveys or reports
Information Risk Management Program
DAI-IRSA Program
Resources | Tools | Training | Guidance
Determine Approach
Conduct
Assessment
Consult
Reports

## Timeline
Reports are updated weekly.
Mid-November | DAI-IRSA Surveys available
End-November | Unit Reports available
Mid-December | Divisional and Unit Status Reports available
Mid-January | Dean/Divisional Summary Reports
End-January | Units complete inventory and assessments & mark surveys as complete by end of January
End-Feburary | Dean and / or Unit Heads approve Information Risk Management Programs by end of February
Divisional/Unit Planning
Complete Assessments & IRMP
Nov. 1, 2021 - Jan. 31, 2022
Dean / Head Approval
IRMP Review & Approval

## Unit Planning
Anticipated Completion Date:
2022-01-31
Unit Approval:
Name | Contact
Inventory and Assessment Coordinator
Name | Contact
Access to unit reports
Name | Contact
d
Academic and administrative unit heads shall be responsible for assuring the protection of Digital Assets within their units in accordance with this Policy and associated Procedures and Standards...(and) develop an Information Risk Management Program appropriate to the circumstances of the unit, to be approved by the unit head. - Policy on Information Security and the Protection of Digital Assets
Who will approve the Information Risk Management Program for your department or unit?
Approvers will be asked to assert they have reviewed the IRMP for your unit and have approved the program.
Who in your Department or Unit will be responsible for collecting and compiling responses from members of your Department or Unit?
Who in your Department or Unit should have access to the Unit Risk Scorecard and Data Asset Inventory Dashboard on the Tableau server?
See https://uoft.me/dai-irsa-reports for examples

## IRSA
Purpose of this worksheet: | Identify the appropriate respondent for those risk areas in which your unit has activities
Information Risk Categories
Risk Category | Description | Does your unit manage any activities in this area? | Who in your unit should respond in the IRSA? This may be the person who makes decisions about these areas and / or is performing the day-to-day activities in this area
MANAGEMENT RISK | Information Risk Management Program Please see Policy on Information Security and Protection of Digital Assets | Yes
BUSINESS RISK | Credit card data security (when acting as a merchant) and business continuity planning
PURCHASING RISK | Vendor and contract management for technology services that interact with unit and institutional data
HUMAN RESOURCES RISK | Onboarding/off-boarding/cross-boarding processes
FACILITIES RISK | Management of access to physical spaces where technology and data assets reside
LEGAL RISK | Unit awareness of legal, regulatory and contractual requirements | Yes
INSTITUTIONAL DATA RISK | Administrative data management | Yes
RESEARCH DATA RISK | Research data management awareness
INFORMATION TECHNOLOGY RISK
IT1 - Disaster-related risk | System and data backups and disaster recovery processes
IT2 - Infrastructure-related risk | Protection and management of physical spaces related to IT infrastructure (e.g. Data Centres, server rooms, network closets) managed by your unit
IT3 - Network-related risk | Protection and management of networks and network devices (e.g. firewalls, routers, switches, etc.) managed by your unit
IT4 - Server-related risk | Protection and management of sever systems managed by your unit
IT5 - Identity-related risk | Protection and management of identity, credentials, and privileged access | Yes
IT6 - Malicious software risk | End-point protection on servers, desktops and mobile systems managed by your unit
IT7 - Application-related risk | Risk management in application development
IT8 - Development process-related risk | Risk management in the software development life-cycle
IT10 - Client-related risk | Protection and mangement of client systems (desktops, workstations, laptops)
IT11 - Mobile worker-related risk | Implementation of secure remote work practices | Yes
IT12 - Message service-related risk | Secure configuration of email and other collaboration platforms
IT13 - Web-related risk | Web application security
IT14 - Security incident-related risk | Development and maintenance of incident response plans | Yes
IT15 - Storage media-related risk | Secure configuration and destruction of storage media
IT16 - User-related risk | Security awareness training programs in you unit or department | Yes
IT17 - Information asset risk | Management of your data and information system inventories | Yes
IT18 - Software License risk | Management and maintenance of software usage.

## DAI
Purpose: Identify the types of data your unit manages |  |  | Purpose: Identify important assets to include in your unit's data asset inventory
Does your Unit/Department collect, store or process data in any of the following areas: |  |  | List your unit's important data assets and the individual(s) who can provide the information about that asset. For each asset, complete a data asset inventory form in the DAI-IRSA survey tool in REDCap
Subject Area | Examples | Does your unit manage any data in this area? (Yes/No) | Data Asset | Who in your unit is the expert for this Data Asset?
Alumni | lists, demographics, activity
Donors | lists, demographics, activity
Faculty | lists, demographics, activity
Staff | lists, demographics, activity (including applicants)
Financial | transactions and activity; budgets, accounting, financial planning, charges, invoices, etc.
IT Management & Service Delivery | T-Card, , Wi-Fi, cofiguration files, network & flow diagrams, source code, support tickets, change log, IAM & auth assets
Facilities Management | construction, maintenance, physical/building access, floor plans and diagrams
Scholarly Research Administration | data about administration of research activity, e.g. RIS
Scholarly Research Data | data collected and used in research projects
Prospective Students | application lists, demographics, activity
Students | lists, demographics, and registration & enrollment activity
Student Life | student housing data, awards, so-curricular, career and advising services, accessibility services, student surveys
Curriculum management | curses, curriculum, degrees, programs
Library Data | library holdings and activity
Health | patient data, including, medical, mental health and social work